## Sheet4
Row Labels | Count of Months (Due_Date)
In Progress | 9
12-Jul | 1
18-Jul | 1
25-Jul | 1
1-Aug | 1
7-Aug | 1
14-Aug | 1
21-Aug | 1
27-Aug | 1
3-Sep | 1
Grand Total | 9

## TasksTask IDTask ID
#NAME? | Task Name | Description | Owner | Priority | Start Date | Due_Date | Status | Comments | Overdue | Dependencies | Category | Effort Estimate (hours) | Risk
1 | Project kickoff meeting | Organize a meeting to officially start the project and introduce team members. | Alice Johnson | Highest | 2025-07-01 | 2025-07-04 | Complete | Waiting for client feedback. | FALSE | Design Approval | Planning | 1 | Low
2 | Requirements gathering | Collect and document detailed requirements and expectations from the client. | Bob Smith | Very High | 2025-07-02 | 2025-07-05 | Complete | Task completed ahead of schedule. | FALSE | Requirements Finalized | Design | 2 | Medium
3 | Stakeholder interviews | Interview key stakeholders to understand objectives and constraints. | Carol Lee | High | 2025-07-03 | 2025-07-06 | Complete | Need clarification on requirements. | FALSE | Database Migration Complete | Development | 3 | High
4 | Define project scope | Clearly define the boundaries and deliverables of the project. | David Brown | High-Medium | 2025-07-04 | 2025-07-08 | On Hold | Design approved by team. | FALSE | QA Testing | Testing | 4 | Critical
5 | Develop project plan | Develop a comprehensive plan outlining timelines, milestones, and resources. | Emma Watson | Medium-High | 2025-07-05 | 2025-07-09 | In Review | Blocked due to resource unavailability. | FALSE | Client Feedback Received | Deployment | 5 | Minimal
6 | Assign team roles | Assign responsibilities and roles to each team member for clarity and accountability. | Frank Martin | Upper Medium | 2025-07-06 | 2025-07-10 | Not Started | Database migration scheduled for next week. | FALSE | User Story #12 | Documentation | 6 | Moderate
7 | Set up project workspace | Set up a shared workspace or digital platform for project collaboration. | Grace Kim | Medium | 2025-07-07 | 2025-07-12 | In Progress | Code review pending. | FALSE | Data Entry Completed | Research | 7 | Significant
8 | Create initial design mockups | Create visual mockups to represent the initial design concepts. | Henry Clark | Medium-Low | 2025-07-08 | 2025-07-13 | Complete | Testing phase delayed by one day. | FALSE | API Integration | Review | 8 | None
9 | Review design with team | Present the design mockups to the team for review and discussion. | Isabella Turner | Low-Medium | 2025-07-09 | 2025-07-14 | On Hold | Documentation needs update. | FALSE | Backend Deployment | Bug Fix | 9 | Manageable
10 | Gather feedback | Gather feedback from the team to refine designs and address concerns. | Jack Wilson | Low | 2025-07-10 | 2025-07-16 | In Review | Stakeholder approval required. | FALSE | Bug Fix #17 | Feature | 10 | Elevated
11 | Revise design | Incorporate feedback and make necessary design revisions. | Kelly Young | Very Low | 2025-07-11 | 2025-07-17 | Not Started | Issue escalated to management. | FALSE | Vendor Delivery | Enhancement | 12 | Severe
12 | Prepare technical specifications | Prepare detailed technical specifications to guide development. | Liam Harris | Lowest | 2025-07-12 | 2025-07-18 | In Progress | Awaiting data from analytics team. | FALSE | Resource Allocation | User Story | 14 | Unknown
13 | Database setup | Set up the necessary database structure for the project. | Mia Robinson | Critical | 2025-07-13 | 2025-07-20 | Complete | All dependencies resolved. | FALSE | Project Kickoff Meeting | Epic | 16 | Acceptable
14 | Develop frontend | Build the user interface and client-side functionality. | Noah Walker | Urgent | 2025-07-14 | 2025-07-21 | On Hold | Training session booked. | FALSE | Prototype Approved | Sprint | 18 | Negligible
15 | Develop backend | Develop the server-side logic and databases. | Olivia King | Immediate | 2025-07-15 | 2025-07-22 | In Review | Minor bugs identified. | FALSE | Feature Implementation | Hotfix | 20 | Major
16 | Integrate frontend and backend | Connect the frontend and backend components for seamless operation. | Paul Wright | Essential | 2025-07-16 | 2025-07-24 | Not Started | Ready for deployment. | FALSE | Stakeholder Signoff | Maintenance | 22 | Minor
17 | API development | Build and document APIs needed for system integration. | Quinn Adams | Important | 2025-07-17 | 2025-07-25 | In Progress | Post-launch monitoring in progress. | FALSE | Security Review | Refactoring | 24 | Under Review
18 | Unit testing | Test individual components to ensure they function as intended. | Rachel Scott | Significant | 2025-07-18 | 2025-07-26 | Complete | Additional resources allocated. | FALSE | Legal Approval | Integration | 26 | Pending Assessment
19 | QA testing | Conduct quality assurance testing to identify and resolve defects. | Sam Green | Major | 2025-07-19 | 2025-07-28 | On Hold | User training completed. | FALSE | Content Finalized | Training | 28 | Mitigated
20 | User acceptance testing | Perform testing with end users to ensure requirements are met. | Tina Lewis | Moderate | 2025-07-20 | 2025-07-29 | In Review | Change request submitted. | FALSE | Sprint Planning | Support | 30 | Unmitigated
21 | Bug fixing | Identify, log, and resolve software bugs found during testing. | Umar Patel | Normal | 2025-07-21 | 2025-07-30 | Not Started | Meeting with client scheduled. | FALSE | Task 10, Task 11 | Meeting | 32 | Potential
22 | Security review | Review the system for potential security vulnerabilities. | Victoria Evans | Routine | 2025-07-22 | 2025-08-01 | In Progress | Task reprioritized due to new deadline. | FALSE | Design Document Submitted | Demo | 34 | Confirmed
23 | Data migration | Move necessary data from old systems to the new environment. | William Hall | Minor | 2025-07-23 | 2025-08-02 | Complete | Status updated after team meeting. | FALSE | Test Cases Created | Migration | 36 | Possible
24 | Deploy to staging | Deploy the application to a staging environment for final testing. | Xander Baker | Trivial | 2025-07-24 | 2025-08-03 | On Hold | QA passed, moving to next phase. | FALSE | Hardware Setup | Security | 38 | Probable
25 | Staging environment review | Review the staging environment to ensure readiness for launch. | Yolanda Perez | Deferred | 2025-07-25 | 2025-08-05 | In Review | Blocked by pending integration. | FALSE | Milestone 1 Complete | Optimization | 40 | Imminent
26 | Prepare user documentation | Write user manuals and documentation for the system. | Zachary Hill | Scheduled | 2025-07-26 | 2025-08-06 | Not Started | Final edits required. | FALSE | Dependency on External Team | Code Review | 42 | Rare
27 | Conduct training session | Lead a training session to teach users how to operate the system. | Natalie Cooper | Backlog | 2025-07-27 | 2025-08-07 | In Progress | Review meeting postponed. | FALSE | Awaiting Budget Approval | UX/UI | 44 | Frequent
28 | Finalize deployment plan | Finalize the plan for deploying the project to production. | Ethan Reed | Optional | 2025-07-28 | 2025-08-09 | Complete | Awaiting access credentials. | FALSE | UI Mockups Ready | Analytics | 46 | Occasional
29 | Go-live / production deployment | Deploy the project to the live/production environment. | Sophia Murphy | Desirable | 2025-07-29 | 2025-08-10 | On Hold | No issues reported so far. | FALSE | Development Complete | Release | 48 | Possible Impact
30 | Post-deployment testing | Conduct tests after deployment to ensure the system works as expected. | Benjamin Kelly | Requested | 2025-07-30 | 2025-08-11 | In Review | Requires additional testing. | FALSE | App Store Approval | Feedback | 50 | Low Likelihood
31 | Monitor system performance | Monitor the system’s performance post-launch and address issues. | Chloe Foster | Pending | 2025-07-31 | 2025-08-13 | Not Started | Team member on leave. | FALSE | Beta Testing | Procurement | 55 | High Likelihood
32 | Collect user feedback | Collect feedback from users to guide future improvements. | Alice Johnson | Blocker | 2025-08-01 | 2025-08-14 | In Progress | Budget approval received. | FALSE | Content Upload | Configuration | 60 | Low Impact
33 | Issue resolution | Address and resolve any issues reported by users. | Bob Smith | Showstopper | 2025-08-02 | 2025-08-15 | Complete | Documentation finalized. | FALSE | Performance Testing | Data Entry | 65 | High Impact
34 | Update documentation | Update user and technical documentation as changes occur. | Carol Lee | P1 | 2025-08-03 | 2025-08-17 | On Hold | Security review in progress. | FALSE | Infrastructure Ready | Import/Export | 70 | Operational
35 | Conduct project review meeting | Hold a meeting to review the project’s outcomes and lessons learned. | David Brown | P2 | 2025-08-04 | 2025-08-18 | In Review | Action items assigned. | FALSE | Specification Signed Off | Setup | 75 | Financial
36 | Archive project files | Archive all project-related files and documents for future reference. | Emma Watson | P3 | 2025-08-05 | 2025-08-19 | Not Started | Client requested changes. | FALSE | Contract Signed | Onboarding | 80 | Strategic
37 | Prepare final report | Prepare a final report summarizing project results and insights. | Frank Martin | P4 | 2025-08-06 | 2025-08-21 | In Progress | Task merged into main workflow. | FALSE | Wireframes Delivered | Risk Assessment | 85 | Compliance
38 | Celebrate project success | Celebrate the successful completion of the project with the team. | Grace Kim | P5 | 2025-08-07 | 2025-08-22 | Complete | Reviewing feedback from users. | FALSE | Brand Assets Received | QA | 90 | Safety
39 | Plan next phase | Plan for the next project phase or follow-up activities. | Henry Clark | Top | 2025-08-08 | 2025-08-23 | On Hold | Follow-up needed with vendor. | FALSE | Training Scheduled | UAT | 95 | Technical
40 | Conduct retrospective | Conduct a retrospective to reflect on successes and improvements. | Isabella Turner | Secondary | 2025-08-09 | 2025-08-25 | In Review | Delayed due to technical issues. | FALSE | Compliance Check | Approval | 100 | Schedule
41 | Create marketing materials | Develop marketing materials to promote the project or product. | Jack Wilson | Tertiary | 2025-08-10 | 2025-08-26 | Not Started | Preparing summary report. | FALSE | Cloud Resources Provisioned | Compliance | 120 | Resource
42 | Launch marketing campaign | Launch a marketing campaign to increase awareness. | Kelly Young | Nonessential | 2025-08-11 | 2025-08-27 | In Progress | No further action required. | FALSE | Partner API Ready | Presentation | 140 | External
43 | Update website content | Update the website with new project information or content. | Liam Harris | Nice to Have | 2025-08-12 | 2025-08-29 | Complete | Risk assessment completed. | FALSE | Marketing Plan Approved | Budget | 160 | Internal
44 | Social media announcement | Announce the project or product launch on social media. | Mia Robinson | Fast Track | 2025-08-13 | 2025-08-30 | On Hold | Task closed after verification. | FALSE | Release Notes Written | Stakeholder | 180 | Reputational
45 | Analyze project metrics | Analyze project metrics to measure success and impact. | Noah Walker | Standard | 2025-08-14 | 2025-08-31 | In Review | Progress slower than expected. | FALSE | Localization Complete | Resource Allocation | 200 | Market
46 | Prepare budget report | Prepare a financial report detailing the project budget and expenses. | Olivia King | Just in Time | 2025-08-15 | 2025-09-02 | Not Started | Next steps discussed with team. | FALSE | Documentation Updated | Monitoring | 220 | Legal
47 | Invoice client | Create and send invoices to clients or stakeholders. | Paul Wright | Accelerated | 2025-08-16 | 2025-09-03 | In Progress | Resources reallocated. | FALSE | Purchase Order Approved | Research Spike | 240 | Political
48 | Close project | Officially close the project and communicate completion to stakeholders. | Quinn Adams | Expedite | 2025-08-17 | 2025-09-04 | Complete | Task marked as urgent. | FALSE | Customer List Finalized | Collaboration | 260 | Environmental
49 | Collect testimonials | Collect testimonials from clients or users for future reference. | Rachel Scott | Hold | 2025-08-18 | 2025-09-06 | On Hold | Awaiting final sign-off. | FALSE | Support Handover | Finalization | 280 | Regulatory
50 | Submit project for awards | Submit the completed project for relevant industry awards. | Sam Green | Waitlist | 2025-08-19 | 2025-09-07 | In Review | Task split into subtasks. | FALSE |  | Retrospective | 300 | Emerging